## Sheet1
Level 1 | Level 2 | Level 3 | Level 4 | prioritization | stack rank | Days
|  |  | Zodiac Dragon design | High | 1 | 20
|  |  | Horse desigh | High | 2 | 10
|  |  | Tigher design | Medium | 29 | 10
|  |  | Monkey design | Medium | 30 | 7
|  | Twelve animals cartoon design | Pig design | Medium | 31 | 7
|  |  | Rabbit desigh | Medium | 32 | 7
|  |  | Sheep design | Medium | 34 | 7
|  |  | Snake design | Medium | 35 | 7
|  |  | Rosster design | Medium | 36 | 7
|  |  | Oxen design | Medium | 37 | 7
|  |  | Rat design | Medium | 38 | 7
|  |  | Dog design | Medium | 39 | 7
|  | Storage design |  | High | 22 | 4
|  | Screen design |  | High | 23 | 1
|  | Interface design |  | High | 24 | 5
|  | Music player circuit design |  | High | 25 | 7
| Hardware | Recorder circuit design |  | High | 26 | 7
|  | Light circuit design |  | Medium | 27 | 7
|  | light design |  | Medium | 28 | 3
Zodiac Music Toy
| Software | Music player | music plays functions | High | 3 | 7
|  |  | play setting | High | 13 | 5
|  |  | create playlist(s) | Medium | 8 | 5
|  |  | add music files into a playlist | Medium | 9 | 5
|  |  | remove the music files from a playlist | Medium | 10 | 5
|  |  | display playlists | Low | 11 | 5
|  |  | playlist selection | Low | 12 | 5
|  |  | copy music/songs | High | 4 | 5
|  |  | delete music/songs | High | 6 | 5
|  |  | sound fades out gradually | High | 7 | 5
|  |  | Volume adjust | High | 5 | 5
|  | Recorder | record | High | 14 | 10
|  |  | copy /move record files to computer | High | 16 | 5
|  |  | erase the record files | Medium | 17 | 5
|  |  | play record file | Low | 18 | 5
|  |  | Volume adjust | High | 15 | 5
|  | light | setting the color | low | 21 | 5
|  |  | setting the time to fade out | Medium | 20 | 5
|  |  | light fades out gradually | High | 19 | 5
|  | test | music plays functions | High | 40 | 4
|  |  | play setting | High | 50 | 4
|  |  | create playlist(s) | Medium | 43 | 3
|  |  | add music files into a playlist | Medium | 44 | 3
|  |  | remove the music files from a playlist | Medium | 45 | 3
|  |  | display playlists | Low | 46 | 3
|  |  | playlist selection | Low | 47 | 3
|  |  | copy music/songs | High | 41 | 3
|  |  | delete music/songs | High | 49 | 3
|  |  | sound fades out gradually | High | 48 | 3
|  |  | Volume adjust | High | 42 | 3
|  |  | record | High | 51 | 4
|  |  | copy /move record files to/from a computer | High | 53 | 3
|  |  | erase the record files | Medium | 54 | 3
|  |  | play record file | Low | 55 | 3
|  |  | Volume adjust | High | 52 | 3
|  |  | setting the color of light | low | 58 | 4
|  |  | setting the time to fade out | Medium | 57 | 3
|  |  | light fades out gradually | High | 56 | 3